## Project Planner
VTOL Aircraft
Production of a vertical take-off and landing aircraft process |  |  | Period Highlight: |  | 3 |  | Plan Duration |  |  | Actual Start |  |  | % Complete |  |  | Actual |  | % Complete (beyondplan)
ACTIVITIES | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Researh about FDM Printing Methods | 1 | 2 | 1 | 2 | 100%
Market Research for Electronic Components | 2 | 1 | 2 | 1 | 100%
Market Research for Composite Pipes, Fasteners and Adhesives | 2 | 1 | 2 | 1 | 100%
Design and Manufacturing Control Surfaces | 3 | 3 | - | - | 0%
Designation of Fuselage Compartments | 3 | 3 | - | - | 0%
Manufacturing of the Wings | 6 | 3 | - | - | 0%
Manufacturing of the Tail | 6 | 3 | - | - | 0%
Manufacturing of the Fuselage | 8 | 3 | - | - | 0%
Manufacturing of Tilt Mechanism | 10 | 1 | - | - | 0%
Prototypeing of Tilt Mechanism | 10 | 2 | - | - | 0%
Assembly of the Actuators and Tilt Mechanism | 11 | 2 | - | - | 0%
Assembly of the Aircraft | 12 | 2 | - | - | 0%
Electronic Connections and Wiring of Electronics | 12 | 2 | - | - | 0%
Software Configuration and Maiden Flight | 13 | 3 | - | - | 0%