## Project Planner
VTOL Aircraft
Production of a vertical take-off and landing aircraft process |  |  | Period Highlight: |  | 4 |  | Plan Duration |  |  | Actual Start |  |  | % Complete |  |  | Actual |  | % Complete (beyondplan)
ACTIVITIES | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 10.02 - 16.02 | 17.02 - 23.02 | 24.02 - 02.03 | 24.02 - 02.03 | 03.03 - 09.03 | 10.03 - 16.03 | 17.03 - 23.03 | 24.03 - 30.03 | 31.03 - 06.04 | 07.04 - 13.04 | 14.04 - 20.04 | 21.04 - 27.04 | 28.04 - 04.05 | 05.05 - 11.05 | 12.05 - 18.05
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Researh about FDM Printing Methods | 1 | 2 | 1 | 2 | 100%
Market Research for Electronic Components | 2 | 1 | 2 | 1 | 100%
Market Research for Composite Pipes, Fasteners and Adhesives | 2 | 1 | 2 | 1 | 100%
Design and Manufacturing Control Surfaces | 3 | 3 | 3 | - | 30%
Designation of Fuselage Compartments | 3 | 3 | - | - | 0%
Manufacturing of the Wings | 6 | 3 | - | - | 0%
Manufacturing of the Tail | 6 | 3 | - | - | 0%
Manufacturing of the Fuselage | 8 | 3 | - | - | 0%
Manufacturing of Tilt Mechanism | 10 | 1 | - | - | 0%
Prototypeing of Tilt Mechanism | 10 | 2 | - | - | 0%
Assembly of the Actuators and Tilt Mechanism | 11 | 2 | - | - | 0%
Assembly of the Aircraft | 12 | 2 | - | - | 0%
Electronic Connections and Wiring of Electronics | 12 | 2 | - | - | 0%
Software Configuration and Maiden Flight | 13 | 3 | - | - | 0%